## Sheet1
USER STORIES | Story Points(hours) | estimated hrs | Sprints | stories remaining | Days | Hrs Remaining
As a new user, I am required to add my personal information to the website so that I can access the website. | 8 |  | 0 | 14 | 1 | 24
As an existing user I would like to login to my account to continue with my progress | 4 |  | 1 | 7 | 2 | 23
As a user who has just created an account I would like to enter my weight, height , age , gender and body type details so that the website can provide the best optimized help to me. |  | 6 | 2 | 3 | 3 | 21
As a fitness enthusiast, I would like to know my BMI so that i can know if i am healthy or overweight or underweight. | 4 |  | 3 | 1 | 4 | 20
As an unaware user. I would like to learn about proper workout technique through video tutorials so that I can avoid injuries and get the right form. | 6 |  | 4 | 0 | 5 | 18
As a workout enthusiast user, I would like to know about specific exercises for muscle groups so that I can work out with the best efficiency and get the most gains out of my workout session. | 7 |  |  |  | 6 | 18
As a logged in user concerned user, I would like to choose a workout plan based on my schedule from beginners or intermediate/expert so that I can follow a regulated plan for my workouts. |  | 4 |  |  | 7 | 15
As a health concerned user, I would like to describe my body goals so that I can get specific diet suggestions and know my requirements like calorie intake and exercise for achieving my body goal. |  | 8 |  |  | 8 | 14
As a regular user, I would like to know more about where I stand in the whole process, so that I can better align myself to achieve my goals. |  | 7 |  |  | 9 | 11
As a health concerned user I would like to track my calorie intake, so that i can understand and moderate how much calories i am eating per day. | 5 |  |  |  | 10 | 8
As a regular user, I would like to know healthy meal options which I can eat, so that I can lower ,higher or maintain my overall caloric intake. |  | 6 |  |  | 11 | 4
As a health concerned user I would like to lose some weight so that i can stay fit, healthy and active. |  | 9 |  |  | 12 | 1
As an inexperienced user I would like to know if there are any supplements that will help me fulfill my daily body needs. |  | 4 |  |  | 13 | 0
As a fitness beginner I would like get popup notifications about helpful articles so that I get to know about useful information that would be helpful for my fitness journey. |  | 11
Velocity= 34